## Hours
Soil Health Case Study Tool Kit:
Tasks & Hours Estimates to Produce One Case Study
© 2024 American Farmland Trust
Updated May 30, 2024
Tasks | Author/Project Leader (PL) | Project Economist (PE) | Typical Duration &/or Notes
IDENTIFY & SECURE A "SOIL HEALTH SUCCESSFUL FARMER"
Review the Tool Kit, specifically the Introductory Materials | 2 | 1
Watch AFT YouTube training video: "Overview of Training & AFT Project" (14 min) | 0.5 | 0.5 | Note: These videos are from Fall 2020 reviewing the first version of the RSHEC Tool, but the foundational principles of data collection and analysis are the same, just recognize that formatting of documents has changed
Watch video: "Methods to Secure SH Successful Farmers" (18 min) | 0.5 | 0.5
Tailor the Introduction & Consent Form document for Producers to reflect details of your project | 2
Tailor the Criteria Handout defining "soil health successful farmer" | 2
Tailor Section I of the R-SHEC Questionnaire as needed | 1 | 2
Identify a soil health successful farmer contacting your network (email, social media, flyers, etc) | 3
Approach & secure a farmer candidate - call, email, visit potential farmer to confirm farmer meets Criteria by walking thru Intro form & completing Section I of Questionnaire | 2
PL reviews Section I of Questionnaire with PE to ensure farmer meets Criteria | 1 | 1
Gain farmer consent and have sign Intro & Consent Form (optional) | 1
Set up the interview date, time, & location | 1
Identify and test a way to record your interview(s) | 1
Catch-all: Planning, prep, & touch base meetings | 3 | 3
Securing Farmer Total Hours | 18 | 7 | 1-2 months
ECONOMIC ANALYSIS
Review the Tool Kit, specifically the RSHEC Tool, Questionnaire, Manual, and 2024 training video | 2 | 2
Watch AFT YouTube training video: "AFT Soil Health Economic Methods Overview & Questionnaire" (27 min) | 2 | 2 | Note: These videos are from Fall 2020 reviewing the first version of the RSHEC Tool, but the foundational principles of data collection and analysis are the same, just recognize that formatting of documents has changed
Watch video: "SH Economics Calculator & Making Adjustments" (67 min) | 1.5 | 1.5
Tailor the Questionnaire & RSHEC as needed | 5 | 20
Tailor the Questionnaire & RSHEC based on information collected in the pre-interview | 2
Conduct the economic interviews (usually four, one-hour interviews) | 4 | 4
Clean up responses in the Questionnaire - listen to &/or transcribe the recordings | 5
Author reviews the Questionnaire with PE to ensure data is logged correctly and identify missing info or errors | 2 | 2
Follow-up with the farmer to clarify uncertainties and inconsistencies | 3
PE conducts final review of Questionnaire |  | 2
Enter data from the Questionnaire into the RSHEC Tool | 2
Review the results in the RSHEC with Project Economist | 2 | 4
Potential follow-up with farmer following review with Economist | 1
Write more descriptive cost and benefit item details in the to-be-published PBA Table | 1 | 1
Catch-all: Planning, prep, & touch base meetings | 3 | 3
Economic Analysis Total Hours | 33.5 | 39.5 | 1-2 months
WRITING & REVIEW
Review the Tool Kit, specifically the Case Study Writing Guidance | 2 | 1
Watch AFT YouTube training video: "AFT training on writing your own case studies & Q&A" (19 min) | 0.5 |  | Note: These videos are from Fall 2020 reviewing the first version of the RSHEC Tool, but the foundational principles of data collection and analysis are the same, just recognize that formatting of documents has changed
Review writing guidance documents (template, guidance, copy editing tips) | 1
Obtain photos for case study | 1
Write and edit a first draft (aim for 1000 words) | 4
Edit of first draft and review of changes with author | 1 | 4
Follow up with farmer for clarification as needed | 1
Reorder contents of PBA table to follow flow of text | 1
Tailor footnotes to match effects accounted for in case study | 1 | 1
Check text with table to ensure all numbers match | 1 | 2 | Note: Sometimes have to do this more than once as numbers change during review
Create & use an editor's check-list to ensure all components of the case study are satisfied | 1 | 1
Edit case study draft as needed | 2 | 2
We encourage you to have external reviewers (e.g., soil health specialist, ag economist) | 6
Clean up the Questionnaire & the Calculator to prepare for external review | 2 | 2
Incorporate any reviewer edits | 3
Do follow-up with the farmer if needed to satisfy questions from reviewers | 1
Catch-all: Planning, prep, & touch base meetings | 3 | 3
Writing & Review Total Hours | 29.5 | 15 | 1 to 1.5 months
PUBLICATION
Prepare for publication (e.g., select photos, formatting, etc.) | 2 | 1
Collaborate with a designer | 4
Find additional photos to satisfy designer needs | 1
Arrange printer contract | 3
Catch-all: Planning, prep, & touch base meetings | 3 | 3
Publication Total Hours | 13 | 4 | 2 weeks to 1 month
GRAND TOTAL | 94 | 65.5 | 159.5
Add Contingency1 | 28.2 | 19.65
GRAND TOTAL WITH CONTINGENCY | 122.2 | 85.15 | 207.35
*Total duration estimate ranges between 4 to 6 months start to finish.
1 Contingency = | 30%