## Template
Preparation Checklist for Hosting a Peer to Peer Farmer Gathering
Event Information:
Title/Description: | Date(s): | Location(s): | Team Members Involved:
Task | Lead person | Deadline | Notes | Timeline
Identify key roles: |  |  |  | (8 weeks prior)
-Facilitator/co-facilitator
-Logistics (meeting room, set up, food, registration, handouts, translation/interpretation)
-Outreach (direct mailings, ads, posters, social media, news release, photography, etc.)
-Program (begin to prepare facilitator agenda, set up tour, identify professional experts needed, prepare for demos)
Determine topic
Determine budget for meal, snacks, transportation, speaker stipends |  |  |  | (8 weeks prior)
Book meeting facility |  |  |  | (6 weeks prior)
Identify speakers, including producers/landowners |  |  |  | (6 weeks prior)
Invite professional conservationists |  |  |  | (6 weeks prior)
Create registration or RSVP form |  |  |  | (6 weeks prior)
Create promotional materials |  |  |  | (6 weeks prior)
Advertise and promote |  |  |  | (4 weeks prior)
Identify caterer or discuss how food will be handled |  |  |  | (4 weeks prior)
Confirm attendance of resource professionals, and gather contact info for the follow up Resource List |  |  |  | (3 weeks prior)
Prepare and submit news release to local papers |  |  |  | (2 weeks prior)
Continue to advertise in social media and websites
print off or gather copies of resources to bring to your meeting (handouts, etc.)
Provide tour map to bus company
Visit meeting site and if possible arrange to set up tables in circular or U-shape, a resource table for handouts and tables for snacks/lunch |  |  |  | (1 week prior)
Finalize and make copies of: evaluation forms, sign in sheets, agendas with each attending conservation professionals' contact information on the back |  |  |  | (1 week prior)
Gather together: name tags, markers and card stock for name tents |  |  |  | (1 week prior)
Confirm RSVPs with caterer
Conference call with meeting organizers to go over agenda |  |  |  | (2 business days prior)
Download registration list to take attendance |  |  |  | (1 Day prior or Day-of)
Send follow up materials to participants: |  |  |  | 1-2 days after
Handouts
- Resource List with contact info of speakers |  |  |  | 1-2 days after
- Recording (if online), slides, handouts from the event |  |  |  | 1-2 days after
- Roster of participants for networking |  |  |  | 1-2 days after
- Exit Evaluation Survey |  |  |  | 1-2 days after
- Clean up registration and attendance data and send to National Initiative |  |  |  | 1-2 days after
On the day of the meeting:
-Arrive 30 minutes early to check room set up
-Prepare coffee, tea & breakfast items (if not catered)
-Set up resource table and lay out publications
-Set out blank table tents with markers around the table
-Set up demos
-Get cooler(s) ready for tour
-Greet participants and have fun!
After the meeting:
-Collect and scan evaluation forms
-Collect invoices and pay bills
-Follow up with women who requested assistance
-Send thank you notes to farmers on the tour, professionals (if not local), facility host, sponsor(s)
-Set up a teleconference to debrief with local planning group, discuss next steps & lessons learned
-Send scanned evaluation forms to AFT (AFT will enter data anonymously into national database, summmarize data and return a summary report)